Indiana Aerospace University

Department of Aerospace Engineering

IAU Town Center, Lapu-Lapu City, Cebu, Philippines 6015

The Electronic Power System (EPS) provides power generation, storage, regulation, and distribution for a 3U CubeSat. This timeline presents a structured plan for designing, testing, and validating the EPS, from defining mission requirements to final integration and documentation, ensuring reliable operation in low Earth orbit.

| Date | Phase | Goal | Key Tasks | Deliverables |
| --- | --- | --- | --- | --- |
| Jan 5–7 | Mission & EPS Requirements | Define EPS needs | Review orbit & eclipse, estimate satellite power, define power modes & redundancy | EPS Requirements, Preliminary Power Budget |
| Jan 8–12 | EPS Architecture | Decide power flow | Select EPS type (DET/PPT), main bus voltage, number of solar panels, battery chemistry | EPS Block Diagram, Architecture Analysis |
| Jan 5–15 | Component Procurement | Secure EPS hardware | Purchase solar cells, batteries, controllers, DC-DCs; verify lead times | Procurement List, Purchase Records |
| Jan 5–20 | Solar, Battery & Regulation Design | Design generation, storage & regulation | Solar power calc & selection, battery sizing & protection, charge controller & DC-DC design | Solar/Battery Design, EPS Schematic, Power Rail Doc |
| Jan 21–25 | Simulation & Verification | Validate EPS design | Power flow & worst-case analysis, battery DoD simulation, thermal estimation | Power Simulation Report, Verified Margins |
| Jan 26–Feb 1 | PCB Design & Review | Convert design to hardware | Finalize schematic, PCB layout, add test points, internal review, PCB fabrication (Feb 1) | EPS PCB Files, Design Review Report |
| Feb 2–8 | Assembly & Standalone Testing | Verify EPS standalone | Assemble PCB, bench test solar/battery, verify regulation & protections | Functional Test Report, Stable Power Outputs |
| Feb 9–15 | Integration Testing | Test EPS with CubeSat | Integrate with OBC/payload, measure consumption, startup/brownout tests, eclipse-mode simulation | Integrated Test Results, Updated Power Budget |
| Feb 16–22 | Final Documentation | Make EPS flight-ready | Finalize design docs, create interface/manual, prepare mission review | Final EPS Design, Final Power Budget, Readiness Package |